## List1
Expectations:
Týden → | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Responsible
Modul ↓
Search | [10 empty] | Miroslav Rudišin
Space | [5 empty] | SAT needed
State
Utility | [10 empty] | Jan Kohout
posix
Cost
Filter |  |  |  | Annealing
Heuristic
Report
Goal
IO | [5 empty] | SAT needed
Bookkeeping
Events | [10 empty] | David Löffler
sat/minisat -------------
Annealing -----------
Reality:
Týden → | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Responsible
Modul ↓
Search | [10 empty] | Miroslav Rudišin
Space | [6 empty] | SAT needed |  |  |  | David Löffler, Jan Kohout
State | [10 empty] | Miroslav Rudišin, Kryštof Sýkora, David Löffler
Utility | overdue | [9 empty] | Jan Kohout, David Löffler, Miroslav Rudišin
posix
Cost | [10 empty] | David Löffler, Miroslav Rudišin
Filter |  |  |  |  | Annealing | [5 empty] | David Löffler
Heuristic | [10 empty] | David Löffler
Report | [10 empty] | Yevgeniya Chekh
Goal | [10 empty] | David Löffler
IO | [8 empty] | SAT needed
Bookkeeping | [10 empty] | Yevgeniya Chekh
Events | [10 empty] | David Löffler
sat/minisat
Annealing | [5 empty] | TBA with Bestoun