## Slide 1: Project CASA: Status update – week 11
Supporting Document for first SteerCo Meeting
May 4, 2017
Yevgeniya Chekh, Jan Kohout, David Löffler, Miroslav Rudišin, Kryštof Sýkora, Marek Szeles, Ho Minh Thanh

## Slide 2: Goals for this Meeting
Review code testing progress
Define next steps
Present overview of project status
Review code translating progress

## Slide 3: Project team assesment

## Slide 4: Project Team Update
Team Role | Name | Contact
Project Lead | Marek Szeles | szelemar@fel.cvut.cz
Analyst | Ho Minh Thanh | homintha@fel.cvut.cz
Head of Development | David Löffler | loffldav@fel.cvut.cz
Head of Testing | Kryštof Sýkora | sykorkry@fel.cvut.cz
Developer | Miroslav Rudišin | rudismi1@fel.cvut.cz
Developer | Jan Kohout | kohouj13@fel.cvut.cz
Tester | Yevgeniya Chekh | chekhyev@fel.cvut.cz

## Slide 5: Project status overview

## Slide 6: Project is being steadily updated…

## Slide 7: …and we are still within planned schedule
Feb
Mar
Apr
May
08
09
10
11
12
13
14
15
16
17
18
19
20
21
Development in Java
27. Apr 2017
Testing Phase
Project Scope Analysis
SteerCo Meetings
Documentation Creation
23. Feb 2017
Team Assembly
02. Mar 2017
Proposal Agreement
Testing
CASA Architecture Mapping
Activity
Milestones
25. May 2017
Final outcome
hand-in
Rector day off
We are
here
16. Mar 2017
Start of
Development

## Slide 8: Today we need to:
Resolve change requests
We would like to implement some changes
Discuss translation problems
Series of documents covering the development and code of the created Java CASA derivative
Revise testing strategy
Working snippets/ whole project based on the CASA source code

## Slide 9: Development update

## Slide 10: Development progress
CASA
io
include
solver
posix
utility
sat
search
algorithms
annealing
covering
events
Main.C
casa
common
minisat
1
2
3
1.1
2.1
3.1
1.2
2.2
3.2
1.3
1.4
1.5
1.6
1.7

## Slide 11: Full Project View: Last meeting (20.4.2017)
Legend
Not started
In progress
Finished
1
1.3
2
2.1
2.2
3
3.1
3.2
1.7
1.1
1.2
1.5
1.4
1.6
Change request

## Slide 12: Full Project View: Current status (2.5.2017)
Legend
1
1.3
2
2.1
2.2
3
3.1
3.2
1.7
1.1
1.2
1.5
1.4
1.6
Not started
In progress
Finished
Change request

## Slide 13: Testing update

## Slide 14: High-level View
CASA
io
include
solver
posix
utility
sat
search
algorithms
annealing
covering
events
Main.C
casa
common
minisat
1
2
3
1.1
2.1
3.1
1.2
2.2
3.2
1.3
1.4
1.5
1.6
1.7

## Slide 15: Unit testing overview
Legend
1
1.3
2
2.1
2.2
3
3.1
3.2
1.7
1.1
1.2
1.5
1.4
1.6
Not started
In progress
Finished
Change request