## Slide 1: Project CASA: Preliminary Project Review
Supporting Documet for first SteerCo Meeting
March 1, 2017
Authors: Yevgeniya Chekh, Jan Kohout, David Löffler, Kryštof Sýkora, Marek Szeles, Ho Minh Thanh

## Slide 2: Goals for this Meeting
Agree on preliminary schedule for project
Agree on preferred testing strategy
Present overview of project
Define project priorities and use cases

## Slide 3: Project Team
Note: Team Roles are to be shuffled every two weeks.
Team Role | Name | Contact
Project Lead | Marek Szeles | szelemar@fel.cvut.cz
Analyst | Ho Minh Thanh | homintha@fel.cvut.cz
Head of Development | David Löffler | loffldav@fel.cvut.cz
Head of Testing | Kryštof Sýkora | sykorkry@fel.cvut.cz
Developer | Yevgeniya Chekh | chekhyev@fel.cvut.cz
Tester | Jan Kohout | kohoujan@fel.cvut.cz

## Slide 4: Our understanding of the problem
Original assignment
Our analysis thus far
The task is to Rewrite the Open Source "CASA" combinational testing tool to Java.
Project objectives:
  To analyze open source CASA application in C++ and rewrite it to Java.
    Final program should run as fast as original.
Our initial analysis shows, that the CASA source code consists not only of C++ code, but also of parts in C and Makefile:
This is an added layer of complexity to the project, but should not affect completion

## Slide 5: Proposed expected outcome of Project
CASA Project Analysis
A document detailing the structure of the original CASA tool
Development Documentation
Series of documents covering the development and code of the created Java derivative
Working Sample
Working snippets/whole project based on the CASA source code

## Slide 6: Proposed Timeline
Feb
Mar
Apr
May
08
09
10
11
12
13
14
15
16
17
18
19
20
21
Development in Java
27. Apr 2017
Testing Phase
Project Scope Analysis
SteerCo Meetings
Documentation Creation
23. Feb 2017
Team Assembly
02. Mar 2017
Proposal Agreement
Testing
CASA Architecture Mapping
Activity
Milestones
16. Mar 2017
Start of
Development
25. May 2017
Final outcome
hand-in
Rector day off

## Slide 7: CASA Project Tree

## Slide 8: High-level View
CASA
io
include
solver
posix
utility
sat
search
algorithms
annealing
covering
events
Main.C
casa
common
minisat