## RiskList
ID | Risk event | Owner | Probability | Impact | Priority | State | If happened, when? | Risk area | Proposed solution | When | Responsible | Areas impacted |  |  |  | Remark
[12 empty] | Time | Cost | Scope | Quality
R1 | Realization team change | CASA team | High | Low | B | Resolved | Week 2 | Global | Redistribution of project work/Changing project scope | 1 week after change | Project Leader | X | - | X | X
R2 | Not being able to deliver full output | CASA team/Client | High | Medium | B | Resolved | Week 13 | Global | Changing project scope | 1 week before project end | Project Leader | X | - | X | X
R3 | Not being able to translate (parts of) program | CASA team | Medium | Medium | B | Resolved | Week 11 | Global | Asking for external help | 1 week within information | Project Leader | X | - | - | X | Separate document available - External help failed, but solution was found through scope change
R4 | Radical change of requirements | CASA team | Medium | High | C | Resolved | Week 6 | Global | Refusing change request within bounds of project | Immediately | Project Leader | X | - | X | -
R5 | Overall project cancelled | Client | Low | High | B | Closed | - | Global | Change project scope, reflect in final output | Immediately | Project Leader | - | - | X | -
R6 | Development Team member lost | CASA Team | Low | Medium | B | Closed | - | Development | Change project scope, redistribute work | 1 week after change |  | X | - | X | X
R7 | Testing Team member lost | CASA Team | Low | Low | A | Closed | - | Testing | Change project scope, redistribute work | 1 week after change |  | X | - | X | X
R8 | Analysis Team member lost | CASA Team | Low | Low | A | Closed | - | Analysis | Change project scope, redistribute work | 1 week after change |  | X | - | X | X
Note on G1: Author: open/closed
Note on I1: Author: global…

## TaskList
description | owner | deadline | status
updates
date | description |  | status

## ChangeRequests
ID | Date | Minutes relevant | Minutes task ID | Description | Proposed by | Scope | Project Team Proposed action | Accepted? | As proposed by project team? | Note
ChR1 | 2017-03-28 | W6 | - |  | Client - Bestoun S. Ahmed | Global | NO | NO | YES
ChR2 | 2017-03-28 | W6 | - | Program performance is not a priority issue anymore | Client - Bestoun S. Ahmed | Global | YES | YES | YES
ChR3 | 2017-04-06 | W5,W7 | 5.1 | Possibility of running C++ code snippets from Java | CASA Team - Kryštof Sýkora | Development | YES | NO | NO | Separate document analysis available
ChR4 | 2017-04-27 | W10 | - | Simplifying parsing to exclude posix and IO modules | CASA Team - David Löffler | Development | YES | YES | YES | Separate document analysis available
ChR5 | 2017-05-04 | W11 | - | Project acceptance requirement change | CASA Team - Marek Szeles | Global | YES | YES | YES
ChR6 | 2017-05-09 | W12 | - | Project scope can be extended with teammembers participating receiving compensation for finishing of implementation | Client - Miroslav Bureš | Global | YES | Pending | NO
ChR7 | 2017-05-09 | W14 | - | Project scope can be extended with teammembers participating receiving compensation for finishing of implementation | Client - Bestoun S. Ahmed | Global | YES | Pending | NO
Note on H1: Author: NO/YES/Partial
Note on I1: Author: NO/YES/Pending
Note on J1: Author: NO/YES

## KeyDecisions
ID